## Sheet1
The NoTeam Team plan I | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
Group Project Schedule | Week 8: Enh Week; Week 11: First Delverable; Week 13: Xmas!; Week 15: Feedback
Pitch/Concept | Week 5: Everyone
Concept/Design | Week 6: Everyone/Designers
GitHub setup | Week 7: PO/ Scrum
GDD and TDD (20%) | Week 7: Produte Owner and everyone; Week 11: DUE Date
Design/Production (Alpha) | Week 10: Designers / Devs
Asset Design | Week 8: Designers
Animation Design | Week 12: Designers
Pre-Production. | Week 13: Devs
Production (Alpha) | Week 14: Devs
The NoTeam Team plan II | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31
Group Project Schedule | Devs Week 27: Final Deliverable; Devs Week 31: Demo
Production (Beta) | Week 17: Everyone; Week 18: /Devs
Debugging | Week 21: Devs
GDD and TDD Updated (5%) | Week 20: Product Owner
Open Beta Testing | Week 23: Testing
Quality Assurance (10%) | Week 22: Product Owner
Pre-Release(RC 50%)/Docs(15%) | Devs Week 27: Due Date
Presentation (10%) | Devs Week 28: Product Owner and everyone